## Developer fields
ID | Title | Status | Resolved Date | Assignee | Comment | Root cause analysis | Dev fix | Dependency
1 | Top navigation overlaps Executive Overview card and blinks while scrolling | Closed |  | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Changing the header size while scrolling could shift the page and repeatedly trigger its scroll state. | Kept the sticky header bars at a constant height, stabilized scroll detection, and removed the duplicate compact heading. | Manual regression check of the current build
2 | Active status text is displayed in blue instead of green on the Executive Overview dashboard. | Closed |  | Bhanu Pratap Manthena | Existing fix retained after reviewing the current build. Original QA closure is preserved. Please perform the listed regression checks. | The Active badge used the general blue accent instead of the active-state color. | Active assessment badges use green in the dashboard and assessment views. | Manual regression check of the current build
3 | Candidate profile is not added to the assessment after clicking Confirm and Load Candidates. | Closed |  | Bhanu Pratap Manthena
4 | Close (X) icon is partially hidden in the generated candidate assessment report | Closed |  | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Long report header content could crowd the close control on small screens. | Reserved space for the close button and allowed candidate details to wrap. | Manual regression check of the current build
5 | Download PDF button is clickable but the assessment report is not downloading | Closed |  | Bhanu Pratap Manthena | Earlier code fix verified in the current build. Awaiting deployment and manual regression testing. Original QA closure is preserved where already recorded. | The previous download flow did not reliably produce a PDF from the current report content. | The current export creates a PDF from normalized report data using native PDF text and drawing operations. The export path is covered by automated tests. | Manual regression check of the current build
6 | Inspect option in Evaluated Reports displays non-evaluated candidate reports | Closed |  | Bhanu Pratap Manthena
7 | Max Duration field accepts values greater than the maximum allowed limit | Closed |  | Bhanu Pratap Manthena
8 | Monitor displays candidate reports when no reports are in progress | Closed |  | Bhanu Pratap Manthena
9 | Start Date and End Date are incorrectly marked as mandatory fields | Closed |  | Bhanu Pratap Manthena | Existing fix retained after reviewing the current build. Original QA closure is preserved. Please perform the listed regression checks. | Optional assessment date fields were labelled with required-field indicators. | Start and end dates are labelled Optional without required asterisks. | Manual regression check of the current build
10 | Mandatory question configuration fields are not marked as required | Closed |  | Bhanu Pratap Manthena | Existing fix retained after reviewing the current build. Original QA closure is preserved. Please perform the listed regression checks. | Required question settings did not consistently show the required-field indicator. | Added required indicators to question text, question type, duration, and the scoring fields used by BASIC and TECHNICAL rounds. | Manual regression check of the current build
11 | Assessment invitation can be sent after the assessment profile End Date/Time has expired | Closed |  | Bhanu Pratap Manthena
12 | Candidate is unable to access the assessment within the configured interview time slot | Closed |  | Bhanu Pratap Manthena | Workaround or frontend-only change. The provider issue is not confirmed fixed. Original sheet status is preserved. | The app timestamps matched the selected IST window, but provider login checks returned unexpected access decisions. The provider implementation cause is not confirmed. | Added a temporary minimum 24-hour interview window to scheduling forms. This is a workaround and does not repair the provider access checks. | PrimeHire scheduling and access validation
13 | Assessment profiles are not retained after reopening the portal | Closed |  | Bhanu Pratap Manthena
14 | Assessment creation - unable to add MCQ question while creating the assessment | Closed |  | Bhanu Pratap Manthena
15 | Candidate name search | Closed |  | Bhanu Pratap Manthena | We cant directly search candidate name in dashboard try it in candidates and assessments module it is working fine
16 | Profile creation is duplicated | Closed |  | Bhanu Pratap Manthena
17 | Display of "linkedin -style pipeline filter" | Closed |  | Bhanu Pratap Manthena | Existing fix retained after reviewing the current build. Original QA closure is preserved. Please perform the listed regression checks. | The reported filter label included an external platform name. | The current frontend does not contain the reported LinkedIn-style wording. Existing closure is retained. A separate Elite HR page should be checked independently if the wording still appears. | Manual regression check of the current build
18 | Unable to create Basic round assessment profile | Closed |  | Bhanu Pratap Manthena
19 | Assessment creations are not reflected | Closed |  | Bhanu Pratap Manthena
20 | Detailed Feedback and Transcript display the same content | Closed |  | Bhanu Pratap Manthena | Earlier code fix verified in the current build. Awaiting deployment and manual regression testing. Original QA closure is preserved where already recorded. | Evaluator remarks and candidate responses were displayed through overlapping report content paths. | Separated evaluator feedback from spoken transcripts. Detailed Feedback and Transcript now display their respective content. | Manual regression check of the current build
21 | Text is not clearly visible in Dark Mode due to insufficient color contrast | Closed |  | Bhanu Pratap Manthena | Existing fix retained after reviewing the current build. Original QA closure is preserved. Please perform the listed regression checks. | The reported issue concerned low text contrast in dark mode. | The current portal uses a light theme. Its dashboard text is readable in the supported theme. This does not claim support for a separate dark theme. | Manual regression check of the current build
22 | Portal displays Render service loading page before opening the application | Phase2 |  | Bhanu Pratap Manthena | This render screen is temporary for v1 which will be fixed for v2
23 | Unable to create Basic round assessment | Fixed |  | Bhanu Pratap Manthena
24 | Edit exisiting job | Fixed |  | Bhanu Pratap Manthena
25 | Incorrect columns in the Bulk upload | Fixed |  | Bhanu Pratap Manthena
26 | Report generation fails for candidate | Closed |  | Bhanu Pratap Manthena | Resolved by removing the regeneration feature at the product owner's request. This does not claim that the provider regeneration service was repaired. | Report regeneration could fail on provider response identifiers or remain in an analyzing state. | Removed report regeneration from the interface, client code, and mutation routes as requested. Report viewing and PDF download remain available. | Manual regression check of the current build
27 | UI - Sideline is not visible in Light mode | Closed |  | Bhanu Pratap Manthena | Existing fix retained after reviewing the current build. Original QA closure is preserved. Please perform the listed regression checks. | The dashboard heading did not have enough contrast in the light view. | The Performance and Assessment Metrics heading uses visible foreground text in the light theme. | Manual regression check of the current build
28 | Weightage field shows an extra 0 before the entered value. | Closed |  | Bhanu Pratap Manthena
29 | Question prompt/Text field is not marked as required | Closed |  | Bhanu Pratap Manthena | Existing fix retained after reviewing the current build. Original QA closure is preserved. Please perform the listed regression checks. | Required question settings did not consistently show the required-field indicator. | Added required indicators to question text, question type, duration, and the scoring fields used by BASIC and TECHNICAL rounds. | Manual regression check of the current build
30 | Enhancement | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | The same module navigation appeared in several places and used different names. | Kept one navigation surface per screen size and made module names consistent. | Deployment and manual retest
31 | Report remains in Analyzing status for a long time | Closed |  | Bhanu Pratap Manthena | Resolved by removing the regeneration feature at the product owner's request. This does not claim that the provider regeneration service was repaired. | Report regeneration could fail on provider response identifiers or remain in an analyzing state. | Removed report regeneration from the interface, client code, and mutation routes as requested. Report viewing and PDF download remain available. | Manual regression check of the current build
32 | inconsistency in grades in report and Multi-Criteria Evaluation Query Builder | Closed |  | Bhanu Pratap Manthena | Earlier code fix verified in the current build. Awaiting deployment and manual regression testing. Original QA closure is preserved where already recorded. | The filter offered fewer grade choices than the report grading system. | Made filter grades match report grades, including A+, B+, C+, and F, with the same score boundaries. | Manual regression check of the current build
33 | reports - grade wise selection filters are not working | Fixed |  | Bhanu Pratap Manthena | Earlier code fix verified in the current build. Awaiting deployment and manual regression testing. Original QA closure is preserved where already recorded. | Candidate filters used estimated scores and grade boundaries that did not match the report. | Filters now use actual report scores and the exact grade shown in the report. Candidates without the requested metric do not match. | Deployment and manual retest
34 | Mail & Assessment Action - selection tab is not working | Closed |  | Bhanu Pratap Manthena
35 | Custom mail template disappears after page refresh | Closed |  | Bhanu Pratap Manthena | Earlier code fix verified in the current build. Awaiting deployment and manual regression testing. Original QA closure is preserved where already recorded. | Template changes were not consistently retained through the server-backed save and refresh flow. | Template saves wait for the server response. Refreshes load the authoritative server list, including an empty list, rather than relying on local-only changes. | Manual regression check of the current build
36 | MCQ assessment result is not updated after submission | Fixed | 2026-10-10T00:00:00.000Z | Bhanu Pratap Manthena | MCQ report and PDF changes completed on 10 October 2026. Correct, incorrect, and unanswered states are covered by tests. Missing provider question entries remain a separate backend issue. | The report view did not interpret MCQ selected and correct answer IDs or map them to option text. | Added MCQ options and outcome messages to the report and PDF. Correct answers are green, wrong selections are red, and negative or blank answer IDs are treated as unanswered. | Deployment and manual retest
37 | Edit Profile option is displayed twice for the assessment profile | Closed |  | Bhanu Pratap Manthena | Existing fix retained after reviewing the current build. Original QA closure is preserved. Please perform the listed regression checks. | The same profile edit action appeared as both an icon and a menu option. | Kept one profile edit control. The profile menu contains activation actions without another Edit Profile entry. | Manual regression check of the current build
38 | Scrollbar does not scroll the menu when clicked or dragged | Closed |  | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Menus were inside scrolling tables that could cut off their edges. Extra table padding was used to make room for them. | Moved menus outside the table containers, added screen-edge positioning, and removed the extra padding. | Manual regression check of the current build
39 | Existing assessment profile is incorrectly displayed as “Syncing...” | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | A stored setup state was displayed as ongoing progress even when no active request was running. | Removed the persistent Syncing badge and kept genuine failure warnings with Retry. | Deployment and manual retest
40 | overlapping of header and second headline | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Repeated headings and tight spacing made the header area look crowded. | Simplified the header and added clearer spacing while keeping scrolling stable. | Deployment and manual retest
41 | CTA alignment from module to module is uneven | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Module headers used different layouts, so action buttons did not align consistently. | Applied a shared header layout with consistent spacing and a mobile layout. | Deployment and manual retest
42 | All options in three dot popup are not displayed for assessment profile | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Menus were inside scrolling tables that could cut off their edges. Extra table padding was used to make room for them. | Moved menus outside the table containers, added screen-edge positioning, and removed the extra padding. | Deployment and manual retest
43 | Selected time is not highlighted in blue | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | The native time control used browser-dependent selection colors. | Added a shared time picker with blue selection states for hour, minute, and AM or PM. | Deployment and manual retest
44 | Module names are not constant across the portal especially in dashboard | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | The same module navigation appeared in several places and used different names. | Kept one navigation surface per screen size and made module names consistent. | Deployment and manual retest
45 | Filters data is not higlighted | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Filter results were below the visible area, and there was no immediate summary. | Added visible result counts and a direct action to open matching candidates. | Deployment and manual retest
46 | Options in the three-dot popup are partially hidden | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Menus were inside scrolling tables that could cut off their edges. Extra table padding was used to make room for them. | Moved menus outside the table containers, added screen-edge positioning, and removed the extra padding. | Deployment and manual retest
47 | Candidate details in Table columns are not clearly visible on the mobile screen. | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | The wide candidate table was difficult to read on small screens. | Added mobile candidate cards with wrapping text, full schedule details, selection, and actions. | Deployment and manual retest
48 | Content is not correct | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | The filter confirmation message used the wrong wording. | Changed the message to Filter applied. | Deployment and manual retest
49 | Incorrect message displayed when accessing the assessment before the scheduled start time | Phase2 |  | Bhanu Pratap Manthena | Workaround or frontend-only change. The provider issue is not confirmed fixed. Original sheet status is preserved. | The app timestamps matched the selected IST window, but provider login checks returned unexpected access decisions. The provider implementation cause is not confirmed. | Added a temporary minimum 24-hour interview window to scheduling forms. This is a workaround and does not repair the provider access checks. | PrimeHire scheduling and access validation
50 | Candidate can access the assessment before the scheduled start time when the start date is today and end date is tomorrow | Phase2 |  | Bhanu Pratap Manthena | Workaround or frontend-only change. The provider issue is not confirmed fixed. Original sheet status is preserved. | The app timestamps matched the selected IST window, but provider login checks returned unexpected access decisions. The provider implementation cause is not confirmed. | Added a temporary minimum 24-hour interview window to scheduling forms. This is a workaround and does not repair the provider access checks. | PrimeHire scheduling and access validation
51 | Start and End date/time fields are displayed in two sections | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Manual registration and the review list repeated scheduling and candidate entry controls. | Kept candidate entry in the manual form and scheduling in the review list. | Deployment and manual retest
52 | Adding Candidates to the list | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Manual registration and the review list repeated scheduling and candidate entry controls. | Kept candidate entry in the manual form and scheduling in the review list. | Deployment and manual retest
53 | Assessment time is not mentioned | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Profile schedule summaries displayed dates without times. | Included start and end times with the IST timezone. | Deployment and manual retest
54 | user end - unnecessary display | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | A stored setup state was displayed as ongoing progress even when no active request was running. | Removed the persistent Syncing badge and kept genuine failure warnings with Retry. | Deployment and manual retest
55 | Deleted custom mail templates reappear after refreshing the portal | Closed |  | Bhanu Pratap Manthena | Earlier code fix verified in the current build. Awaiting deployment and manual regression testing. Original QA closure is preserved where already recorded. | Refreshing a browser could upload stale cached templates that were missing on the server, recreating deleted templates. | Made refreshes read-only and server-authoritative. Deletes wait for server success, and server deletion markers prevent stale browser records from recreating a deleted template. | Manual regression check of the current build
56 | Delete confirmation popup is partially hidden at the bottom of the page | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Dialogs were positioned inside the workspace, which affected their viewport placement. | Used viewport dialogs with a bounded height and internal scrolling. | Deployment and manual retest
57 | Blank white area appears at the bottom when clicking the three-dot options | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Menus were inside scrolling tables that could cut off their edges. Extra table padding was used to make room for them. | Moved menus outside the table containers, added screen-edge positioning, and removed the extra padding. | Deployment and manual retest
58 | Missing report | Closed |  | Bhanu Pratap Manthena Rahul palamarthi | Workaround or frontend-only change. The provider issue is not confirmed fixed. Original sheet status is preserved. | The reported provider response omitted a question result. Restoring it requires backend investigation. | Corrected MCQ result display and PDF export on the frontend. These changes cannot restore question results omitted from the provider response. | PrimeHire backend report generation
59 | alignment of mail templates | Fixed | 2026-10-12T00:00:00.000Z | Bhanu Pratap Manthena | Code fix completed on 12 October 2026. Local tests and Chrome and Edge layout checks passed. Awaiting deployment and manual retest. | Long template names and badges competed for space inside a fixed dialog. | Allowed template text and badges to wrap and made the dialog scroll within the viewport. | Deployment and manual retest

## Paste guide
Copy developer fields
Prepared | 12 October 2026 from the supplied 59-row bug sheet.
Before pasting | Match the ID order with the original sheet. If rows were reordered, copy by bug ID instead of pasting an entire block. Paste values only.
Status | Copy Developer fields!C2:C60 into original N2:N60.
Date, owner and fix notes | Copy Developer fields!D2:H60 into original R2:V60.
Dependency | Copy Developer fields!I2:I60 into original X2:X60.
QA fields | Closed by is not included. Tester, environment, resources, credentials, descriptions and original test dates are not overwritten by these ranges.
Fixed status | Fixed means the code change is complete. New changes still require deployment and manual testing. Existing Closed statuses are preserved.
Resolved dates | 12/10/2026 is used for new UI fixes with a recorded completion date. The MCQ fix uses 10/10/2026. Earlier unknown dates remain blank rather than being invented.
Assignee | Existing owners are preserved. Blank assignee for bug 39 uses Bhanu Pratap Manthena, the existing primary developer in the supplied sheet. Review that owner before pasting.
Unresolved provider issues | Bugs 12, 49 and 50 have a temporary scheduling workaround. Bug 58 needs provider report follow-up. Their original statuses are preserved and their notes explicitly state they are not confirmed fixed.
Other rows | Rows outside the reviewed fixes retain the supplied developer values. No new fix is claimed for them.
Validation | 155 frontend tests, TypeScript and the production build passed. Chrome and Edge each passed 29 local UI checks. Physical Android and deployed portal testing remain pending.
Writing | Developer notes use plain language without em dashes.
Source | User-supplied pasted bug sheet and completed code changes in this conversation. The live Google Sheet was not modified.