## Open and reopened
ID | Title | Original Status | Developer review | Comment | Root cause analysis | Dev fix
39 | Existing assessment profile is incorrectly displayed as “Syncing...” | Open | Ready for manual retest | Existing assessment cards no longer show a persistent Syncing label. Genuine setup failures still show a warning and Retry action. | A stored setup state was displayed as ongoing progress even when no active request was running. | Removed the persistent Syncing badge and kept genuine failure warnings with Retry.
40 | overlapping of header and second headline | Re-open | Ready for manual retest | Header spacing has been improved and the duplicate compact heading has been removed. | Repeated headings and tight spacing made the header area look crowded. | Simplified the header and added clearer spacing while keeping scrolling stable.
41 | CTA alignment from module to module is uneven | Re-open | Ready for manual retest | Module headers now share consistent spacing and action-button alignment, with a stacked layout on smaller screens. | Module headers used different layouts, so action buttons did not align consistently. | Applied a shared header layout with consistent spacing and a mobile layout.
42 | All options in three dot popup are not displayed for assessment profile | Open | Ready for manual retest | Profile and candidate menus are positioned outside scrolling containers so their available options remain visible. | Menus were inside scrolling tables that could cut off their edges. Extra table padding was used to make room for them. | Moved menus outside the table containers, added screen-edge positioning, and removed the extra padding.
43 | Selected time is not highlighted in blue | Open | Ready for manual retest | Selected hour, minute, and AM or PM values are highlighted in blue in the shared time picker. | The native time control used browser-dependent selection colors. | Added a shared time picker with blue selection states for hour, minute, and AM or PM.
44 | Module names are not constant across the portal especially in dashboard | Open | Ready for manual retest | Module names are consistent across the portal, with one navigation surface for each screen size. | The same module navigation appeared in several places and used different names. | Kept one navigation surface per screen size and made module names consistent.
45 | Filters data is not higlighted | Open | Ready for manual retest | Applied filters immediately show matching record counts and provide a direct action to open the filtered candidate directory. | Filter results were below the visible area, and there was no immediate summary. | Added visible result counts and a direct action to open matching candidates.
46 | Options in the three-dot popup are partially hidden | Open | Ready for manual retest | Candidate action menus fit the available viewport and scroll internally when necessary. | Menus were inside scrolling tables that could cut off their edges. Extra table padding was used to make room for them. | Moved menus outside the table containers, added screen-edge positioning, and removed the extra padding.
47 | Candidate details in Table columns are not clearly visible on the mobile screen. | Open | Ready for manual retest | Mobile screens display readable candidate cards with full details, schedules, selection, and available actions. | The wide candidate table was difficult to read on small screens. | Added mobile candidate cards with wrapping text, full schedule details, selection, and actions.
48 | Content is not correct | Open | Ready for manual retest | The confirmation message now says Filter applied. | The filter confirmation message used the wrong wording. | Changed the message to Filter applied.
51 | Start and End date/time fields are displayed in two sections | Open | Ready for manual retest | Manual registration collects candidate details only. Start and end schedules are entered once in the review list. | Manual registration and the review list repeated scheduling and candidate entry controls. | Kept candidate entry in the manual form and scheduling in the review list.
52 | Adding Candidates to the list | Open | Ready for manual retest | The duplicate Add Candidate controls below the review list have been removed. Candidate entry remains in the manual registration form. | Manual registration and the review list repeated scheduling and candidate entry controls. | Kept candidate entry in the manual form and scheduling in the review list.
53 | Assessment time is not mentioned | Open | Ready for manual retest | Assessment profile windows now show both dates and times in IST. | Profile schedule summaries displayed dates without times. | Included start and end times with the IST timezone.
54 | user end - unnecessary display | Open | Ready for manual retest | The persistent Syncing display has been removed. Genuine setup errors remain visible with a Retry action. | A stored setup state was displayed as ongoing progress even when no active request was running. | Removed the persistent Syncing badge and kept genuine failure warnings with Retry.
56 | Delete confirmation popup is partially hidden at the bottom of the page | Open | Ready for manual retest | Candidate confirmation dialogs appear within the viewport and scroll internally when needed. | Dialogs were positioned inside the workspace, which affected their viewport placement. | Used viewport dialogs with a bounded height and internal scrolling.
57 | Blank white area appears at the bottom when clicking the three-dot options | Open | Ready for manual retest | Action menus no longer require extra space below the table, so opening a menu does not create the blank white area. | Menus were inside scrolling tables that could cut off their edges. Extra table padding was used to make room for them. | Moved menus outside the table containers, added screen-edge positioning, and removed the extra padding.
59 | alignment of mail templates | Re-open | Ready for manual retest | Invitation template names, subjects, and badges wrap within a dialog that fits and scrolls inside the viewport. | Long template names and badges competed for space inside a fixed dialog. | Allowed template text and badges to wrap and made the dialog scroll within the viewport.
60 | Assessment login displays “Something went wrong” when the invitation is sent immediately after assigning a candidate | Open | Needs investigation | The immediate-login failure is not confirmed fixed. The source sheet assigns this issue to Rahul Palamarthi. | Login reportedly fails immediately after assessment setup and works after waiting. The provider-side cause has not been confirmed. | No verified fix is recorded for this issue. Investigate provider setup readiness and capture the failed login response before closing it.
61 | Reschedule issue | Open | Needs investigation | The reschedule failure after editing and resending a TECHNICAL assessment is not confirmed fixed. | The cause is unconfirmed. The supplied report does not include the failing reschedule request or the provider error response. | No verified fix is recorded for this edit-and-resend flow. Reproduce it with the current interview ID and review the provider reschedule response.
62 | Questions and Time arent reflecting after editing the assessment | Open | Needs investigation | Edited questions and timing appear in the portal, but the candidate assessment reportedly retains the initial version. This issue is not confirmed fixed. | The portal and candidate assessment show different versions after editing. The cause of the provider content mismatch has not been confirmed. | No verified fix is recorded for updating an existing candidate interview after an assessment edit. Compare saved assessment details and the linked provider interview content.

## Copy guide
Copy guide
Scope | 20 bugs marked Open or Re-open in the latest pasted sheet. 17 have completed code changes; 3 are not confirmed fixed.
Developer review | Blue means code fix complete and ready for manual retest. Deployment and manual confirmation remain pending. Amber means further investigation is needed.
Three fields to copy | Workbook E:G contains Comment, Root cause analysis, and Dev fix in exactly the same order as original sheet T:V.
Before copying | Match the bug IDs and original row order before using the batch ranges. Paste values only. If the original sheet has been reordered, copy by bug ID.
Status and ownership | Original statuses are preserved for reference. This workbook does not change status, resolved date, assignee, or Closed by.
Not confirmed fixed | Bugs 60, 61, and 62 are included with investigation notes. They should not be marked Fixed or Closed based on this workbook.
Other sheet statuses | Closed, Fixed, Phase2, and blank-status rows are outside this Open and Re-open selection.
Source | Latest user attachment e5058b26-6734-4fda-9c9a-15ec1dc20746/Pasted text.txt, completed UI changes, and the manual retest checklist. Prepared 13 October 2026.
Bug IDs and review | Copy range in this workbook -> destination in original sheet
39 to 48 (retest) | Open and reopened!E2:G11 -> original T40:V49
51 to 54 (retest) | Open and reopened!E12:G15 -> original T52:V55
56 to 57 (retest) | Open and reopened!E16:G17 -> original T57:V58
59 (retest) | Open and reopened!E18:G18 -> original T60:V60
60 to 62 (investigate) | Open and reopened!E19:G21 -> original T61:V63
Original sheet | The live bug sheet was not modified. Copy only the notes you want to transfer.